## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | As a user, I want to upload audio call files so they can be transcribed automatically | MUST HAVE | Deepgram API | Siddhi Dhamal | 3- Completed
S1 | S1 | US-002 | As a user, I want speaker-separated transcripts so I can review conversations clearly | MUST HAVE | Deepgram Nova-2 | Siddhi Dhamal | 3- Completed
S1 | S1 | US-003 | As a user, I want to upload text/chat files so they can be summarized | MUST HAVE | Deepgram Text Intelligence | Gunda Lakshmi Gayathri | 3- Completed
S1 | S1 | US-004 | As a user, I want auto-generated summaries so I save review time | MUST HAVE | Deepgram summarize v2 | Gunda Lakshmi Gayathri | 3- Completed
S2 | S2 | US-005 | As a supervisor, I want empathy scores so I can evaluate agent warmth | MUST HAVE | Groq LLaMA 3.1 8B | Siddhi Dhamal | 3- Completed
S2 | S2 | US-006 | As a supervisor, I want compliance scores so I can check protocol adherence | MUST HAVE | Score 1-10 | Siddhi Dhamal | 3- Completed
S2 | S2 | US-007 | As a supervisor, I want resolution scores so I can track issue resolution | MUST HAVE | Score 1-10 | Siddhi Dhamal | 3- Completed
S2 | S2 | US-008 | As a supervisor, I want customer emotion detection so I understand sentiment | MUST HAVE | 8 emotion categories | Gunda Lakshmi Gayathri | 3- Completed
S2 | S2 | US-009 | As a supervisor, I want satisfaction percentage so I can measure happiness | MUST HAVE | 0-100% with label | Gunda Lakshmi Gayathri | 3- Completed
S2 | S2 | US-010 | As a user, I want fairness analysis so agent evaluation is unbiased | SHOULD HAVE | 4 sub-scores | Sowmya | 3- Completed
S3 | S3 | US-011 | As a user, I want a React dashboard so I can view all metrics in one place | MUST HAVE | Vite + React + Tailwind | Gunda Lakshmi Gayathri,Siddhi Dhamal | 3- Completed
S3 | S3 | US-012 | As a user, I want charts so I can visualize quality trends over time | SHOULD HAVE | Recharts library | Sowmya | 3- Completed
S3 | S3 | US-013 | As a user, I want call history so I can review past uploaded files | SHOULD HAVE | CSV based storage | Sowmya | 3- Completed
S3 | S3 | US-014 | As a user, I want PDF/DOC reports so I can share results with my team | SHOULD HAVE | Per-file reports | Gunda Lakshmi Gayathri | 3- Completed
S3 | S3 | US-015 | As a user, I want batch upload so I can process multiple audio files at once | SHOULD HAVE | Async concurrent | Siddhi Dhamal | 3- Completed
S3 | S3 | US-016 | As a user, I want the app to work on mobile so I can access it anywhere | COULD HAVE | Responsive layout | Gunda Lakshmi Gayathri | 3- Completed
S3 | S3 | US-017 | As a user, I want contextual retrieval on transcripts so I can ask questions about past calls | SHOULD HAVE | LangChain + Pinecone | Sowmya | 3- Completed
S3 | S3 | US-018 | As a user, I want to upload policy documents, go through rag pipeline and can generate the scores | SHOULD HAVE | LangChain + Pinecone | Siddhi Dhamal | 3- Completed
S3 | S3 | US-019 | As a supervisor, I want RAG-powered audit summaries so I can get instant contextual insights | SHOULD HAVE | LangChain + Pinecone | Siddhi Dhamal | 3- Completed
S4 | S4 | US-020 | As admin, I want all servers combined so deployment is simpler | MUST HAVE | FastAPI route merging | Gunda Lakshmi Gayathri | 3- Completed
S4 | S4 | US-021 | As admin, I want cloud deployment so users can access the app anytime | MUST HAVE | Render + Vercel | Gunda Lakshmi Gayathri | 3- Completed
S4 | S4 | US-022 | As admin, I want uptime monitoring so the server stays awake 24/7 | MUST HAVE | UptimeRobot 5min ping | Siddhi Dhamal | 2- In Progress
S4 | S4 | US-023 | As admin, I want IST timestamps so file times are accurate for Indian users | SHOULD HAVE | UTC+5:30 applied | Gunda Lakshmi Gayathri | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 141 | 29 | 31 | 25 | 21 | 21 | 40 | 12 | 11 | 15 | 11 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG ¦ Milestone 1: Weeks 1-2 Setup & Transcription
US-001 | 1 | Set up FastAPI audio server (app.py) | 2026-02-02 | 2026-02-03 | Siddhi Dhamal | Build | 3- Completed | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Integrate Deepgram Nova-2 for audio transcription | 2026-02-03 | 2026-02-04 | Siddhi Dhamal | Integration | 3- Completed | 5 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 3 | Implement speaker diarization (Agent/Customer split) | 2026-02-04 | 2026-02-05 | Siddhi Dhamal | Coding | 3- Completed | 5 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 4 | Set up FastAPI text server (chat_app.py) | 2026-02-05 | 2026-02-06 | Gunda Lakshmi Gayathri | Build | 3- Completed | 5 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 5 | Implement dynamic chat parser for any speaker format | 2026-02-06 | 2026-02-09 | Gunda Lakshmi Gayathri | Coding | 3- Completed | 5 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 6 | Integrate Deepgram Text Intelligence for summaries | 2026-02-09 | 2026-02-09 | Gunda Lakshmi Gayathri | Integration | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 7 | Save per-file transcripts and summaries to disk | 2026-02-09 | 2026-02-10 | Sowmya | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 8 | Large text can chunked in parts and then combinely summary is generated of large text. | 2026-02-09 | 2026-02-10 | Sowmya | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG ¦ Milestone 2: Weeks 3-4 LLM Scoring Engine
US-005 | 9 | Integrate Groq LLaMA 3.1 8B for quality analysis | 2026-02-16 | 2026-02-17 | Siddhi Dhamal | Integration | 3- Completed | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 10 | Build empathy, compliance, resolution scoring (1-10) | 2026-02-17 | 2026-02-19 | Siddhi Dhamal | Coding | 3- Completed | 8 | 0 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 11 | Implement empathy timeline and compliance steps | 2026-02-19 | 2026-02-20 | Siddhi Dhamal | Coding | 3- Completed | 5 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 12 | Build customer emotion detection (8 categories) | 2026-02-20 | 2026-02-23 | Gunda Lakshmi Gayathri | Coding | 3- Completed | 5 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | 13 | Implement satisfaction percentage scoring (0-100%) | 2026-02-23 | 2026-02-23 | Gunda Lakshmi Gayathri | Coding | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | 14 | Add bias/fairness analysis (4 sub-scores) | 2026-02-23 | 2026-02-25 | Sowmya | Coding | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | 15 | Save per-file scores to file_scores folder | 2026-02-25 | 2026-02-26 | Sowmya | Others | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG ¦ Milestone 3: Weeks 5-6 RAG & Dashboards
US-011 | 16 | Build React dashboard with Vite + TailwindCSS | 2026-03-02 | 2026-03-04 | Gunda Lakshmi Gayathri,Siddhi Dhamal | Build | 3- Completed | 8 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | 17 | Add Recharts visualizations for all quality metrics | 2026-03-04 | 2026-03-06 | Sowmya | Coding | 3- Completed | 5 | 0 | 0 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | 18 | Implement call history with timestamp and summary | 2026-03-06 | 2026-03-09 | Sowmya | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | 19 | Build PDF and DOC report download feature | 2026-03-09 | 2026-03-09 | Siddhi Dhamal | Coding | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | 20 | Implement batch audio upload with async processing | 2026-03-09 | 2026-03-11 | Siddhi Dhamal | Coding | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | 21 | Make UI mobile responsive with bottom navigation | 2026-03-11 | 2026-03-12 | Gunda Lakshmi Gayathri | Design | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0
US-016 | 22 | Add localStorage persistence for navigation state | 2026-03-12 | 2026-03-13 | Gunda Lakshmi Gayathri | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0
US-017 | 23 | Integrate LangChain + Pinecone for contextual transcript retrieval | 2026-03-12 | 2026-03-13 | Siddhi Dhamal | Integration | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0
US-018 | 24 | Build RAG-powered audit summary endpoint and connect to dashboard | 2026-03-13 | 2026-03-13 | Siddhi Dhamal | Build | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG ¦ Milestone 4: Weeks 7-8 Alerts & Deployment
US-019 | 25 | Combine all FastAPI servers into single main.py | 2026-03-16 | 2026-03-17 | Siddhi Dhamal | Build | 3- Completed | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-020 | 26 | Deploy backend on Render cloud platform | 2026-03-17 | 2026-03-18 | Siddhi Dhamal | Build | 3- Completed | 3 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-020 | 27 | Deploy frontend on Vercel | 2026-03-18 | 2026-03-19 | Gunda Lakshmi Gayathri | Build | 3- Completed | 3 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-021 | 28 | Set up UptimeRobot monitoring (5 min ping) | 2026-03-19 | 2026-03-20 | Sowmya | Others | 2- In Progress | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-022 | 29 | Fix IST timezone for accurate Indian timestamps | 2026-03-20 | 2026-03-23 | Siddhi Dhamal | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-019 | 30 | Add MIT License to GitHub repository | 2026-03-23 | 2026-03-23 | Sowmya | Others | 3- Completed | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | 31 | Fix per-file transcript for correct PDF/DOC reports | 2026-03-23 | 2026-03-23 | Gunda Lakshmi Gayathri | Coding | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on Deepgram API integration parameters | Conducted a detailed discussion with mentors and team; responsibilities split clearly
Sprint 1 | Day 4 | Confusion on FastAPI routing between audio and text servers | Reviewed FastAPI documentation; split server responsibilities clearly
Sprint 2 | Day 6 | Groq LLM prompt formatting issues causing incorrect scores | Conducted a team debugging session; standardised prompt templates
Sprint 2 | Day 8 | Difficulty identifying edge cases for emotion detection | Conducted research and tested with diverse audio samples
Sprint 2 | Day 10 | Fairness scoring sub-categories not aligned with requirements | Created a priority matrix and reviewed with mentor
Sprint 3 | Day 14 | Recharts visualisations not rendering on mobile screens | Collaborated across team to debug responsive layout issues
Sprint 3 | Day 16 | Batch upload async processing causing timeout errors | Optimised async queue
Sprint 3 | Day 18 | Pinecone index setup taking longer than expected due to embedding configuration | Collaborated to resolve Pinecone API config; RAG integration completed
Sprint 4 | Day 22 | Render cold-start delays affecting UptimeRobot ping results | Scheduled server warm-up strategy; adjusted ping interval

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-02 | 2026-02-13 | Gunda Lakshmi Gayathri | Reviewing audio transcription output regularly | Assuming Deepgram API responses are always structured | Participating in daily stand-ups and code reviews | Scheduled review session with all team members to clarify integration goals
2 | Sprint 1 | 2026-02-02 | 2026-02-13 | Siddhi Dhamal | Documenting speaker diarisation edge cases | Delaying testing of boundary conditions | Maintaining clear API contracts between modules | Created test cases covering all diarisation scenarios
3 | Sprint 1 | 2026-02-02 | 2026-02-13 | Sowmya | Prioritising text chat parser coverage | Rushing through summary integration | Asking for help when stuck on Deepgram config | Completed text server with full test coverage on time
4 | Sprint 2 | 2026-02-16 | 2026-02-27 | Gunda Lakshmi Gayathri | Participating in LLM prompt engineering sessions | Delaying empathy score calibration | Collaborating on scoring rubric design | Completed empathy and compliance scoring; received team feedback
5 | Sprint 2 | 2026-02-16 | 2026-02-27 | Siddhi Dhamal | Writing unit tests for emotion detection pipeline | Skipping edge-case testing for emotion categories | Maintaining focus on LLM output consistency | All 8 emotion categories validated against sample data
6 | Sprint 3 | 2026-03-02 | 2026-03-13 | Gunda Lakshmi Gayathri, Siddhi Dhamal, Sowmya | Participating in dashboard design reviews | Delaying mobile responsiveness fixes | Collaborating on chart component reusability | Dashboard deployed with responsive layout and batch upload working
7 | Sprint 3 | 2026-03-02 | 2026-03-13 | Siddhi Dhamal | Integrating RAG pipeline early in sprint | Underestimating Pinecone setup complexity | Collaborating on LangChain prompt engineering | Successfully integrated LangChain + Pinecone; RAG audit summaries operational
8 | Sprint 4 | 2026-03-16 | 2026-03-24 | Gunda Lakshmi Gayathri, Siddhi Dhamal, Sowmya | Monitoring Render deployment logs proactively | Ignoring cold-start latency issues | Reviewing deployment checklists before releases | System fully deployed; UptimeRobot monitoring active; IST timestamps correct